## Sheet2
RISK ASSESS TEMPLATE
HAZARD # | IDENTIFY HAZARD | HOW WILL THEY BE HARMED | IDENTIFY WHO WILL BE HARMED | IDENTIY THE EXTENT OF THE HARM AND HOW | CURRENT CONTROL MEASURES | LIKELIHOOD | CONSEQUENCES | RISK LEVEL | ADDITONAL CONTROL MEASURES | LIKELIHOOD | CONSEQUENCES | RISK LEVEL
1 | loss of control of the model | model impacting persons | Visitors persons attending at the field. | injury or death | CASA 101 requirements, current MAAA MOP's | 2 | 5 | 10 | Experience level of pilots, limited aircraft in the air, practice flying completed on the Saturday to familarise pilots with the location, all pre flight checks being conducted before flying operations commence. The layout for the Display exceeds all minimum set back distances. | 5 | 1 | 5
2 | loss of control of the model over the eatern end of the runway and playing fields | model impacting persons | persons using the fields | injury or death | CASA 101, 30m rule, MAAA MOP's | 3 | 4 | 12 | sports grounds have been booked to ensure no organised sports scheduled, personell will be located in that area during flying operations to advise memebers of the public and monitor and update the flight line controller of any issues | 1 | 4 | 4
3 | Model crash causing fire | fire damage | Property and possibly persons | destruction of property or injury to persons | monitor any fire restrictions, legislative compliance with flying operations, fire extinguishers on the flight line, contact number for police, fire brigade on hand | 2 | 4 | 8 | area in question has a very low if any fuel load to burn, significant amout of un grassed area and open dirt fields, risk of fire is very low | 1 | 4 | 4
4 | Incursion of manned aircraft into the area during the display | impact with manned aircraft | pilot, damage to the aircraft, damage/ destruction of the model | injury or possible death of pilot, damage to full sized aircraft | operations will be in compliance with the instrument issued, NOTAM issued | 2 | 5 | 10 | Helper/spotter to be assigned to assist the pilot with osituational awarness and monitor for any aircraft in the vicinity, any activity to be reported to the Flight Line Director and models will land or take evasive action | 1 | 5 | 5
5 | Pilot not familiar with local flying conditions | May cause disorientation resulting in collision between full size and model aircraft, damage to property on ground. | Person in full size aircraft, Persons property on ground. | severe injury death damage to property | Pilot to be briefed by club safety officer or experience member re club rules and weather conditions prior to first flight. Briefing member shall monitor the pilots flying ability and level of control until satisfied person is competent. | 2 | 5 | 10 | Helper/spotter to be assigned to assist the pilot with osituational awarness and monitor for any aircraft in the vicinity, any activity to be reported to the Flight Line Director and models will land or take evasive action | 1 | 5 | 5
6 | Mechanical/Technical Failure | Severe Injury Death, damage to property. | Person in full size aircraft, Persons property on ground. | Severe Injury Death, damage to property. | Pilot to conduct a preflight check of aircraft prior to each flight to ensure airworthiness. All control surfaces to be checked to ensure they are operating correctly. Pilot to ensure fail safe is operating prior to flight. Range check of equipment prior to first flight. | 3 | 4 | 12 | No additional controls | 2 | 4 | 8
7 | Radio Interference | Loss of control of model resulting in collision between full size and model aircraft | Person in full size aircraft, Persons property on ground. | Severe Injury Death, damage to property on ground. | Range Check prior to first flight. Fail Safe check. | 2 | 4 | 8 | the display will only have 1-2 aircaraft in the air at any one time | 1 | 4 | 4
8 | Structural failure of aircraft | Loss of control of model resulting in collision between full size and model aircraft | Person in full size aircraft, Persons property on ground. | Severe Injury Death, damage to property on ground. | MAAA MOPs, airworthiness check prior to each flight. Control surfaces check security and direction, failsafe check to ensure operating. | 3 | 4 | 12 | All models will be completing test flight and sight familarisation on Saturday before any public are present | 2 | 4 | 8
9 | loss of control of model | impact with surrounding buildings or motor vehicles | building or spectators vehicles | damage to property | all flight operations are away from these hazards | 2 | 3 | 6 | pilots aware of NO FLY Zones, these hazards are well behind the flight line and pilots | 1 | 3 | 3
10 | Vistors to the flying field, member of public entering flying area | collision between aircraft and visitor | Visitors persons attending at the field. | Medium Injury and damage to property | 30 metre rule and club rules re visitor view areas, public to stay behind safety barrier, other members to ensure non members do not enter flying area | 2 | 3 | 6 | This event is fully ticketed and access to the event is restrictied to the ticket holders only | 2 | 3 | 6
11 | Car Parking | Model aircraft colliding with motor vehicles | Damage to Motor vehicle | minimum damage | Car Park situated further than 30 metres from flight line. MAAA Mops and Club Rules | 2 | 2 | 4 | Parking of vehickle being managed with traffic marshals supervising attending vehicles and public | 1 | 2 | 2